## Sheet1
Activity | Duration | Start Date | End Date
MVP 1: Simulation Environment Setup
Work Package 1.1: Development Environment Setup | 1 day | 2025-02-10 | 2025-02-10
Work Package 1.2: Core Simulation Framework Implementation | 8 days | 2025-02-11 | 2025-02-18
Work Package 1.3: Data Input/Output Modules | 3 days | 2025-02-18 | 2025-02-20
Work Package 1.4: Visualization Module | 3 days | 2025-02-21 | 2025-02-23
Activity 2: Scrum #1 | 2 days | 2025-02-23 | 2025-02-24
MVP 2: Algorithm Implementation & Evaluation
Work Package 2.1: Embedding Policy Implementation | 3 days | 2025-02-25 | 2025-02-27
Work Package 2.2: Redundancy Optimization Algorithm (PSO) | 5 days | 2025-02-28 | 2025-03-04
Work Package 2.3: Performance Metric Calculation | 3 days | 2025-03-05 | 2025-03-07
Activity 3: Scrum #2 | 3 days | 2025-03-08 | 2025-03-10
Work Package 2.4: Algorithm Comparison & Evaluation | 8 days | 2025-03-11 | 2025-03-18
Work Package 2.5: Other Redundancy Optimization Algorithms | 4 days | 2025-03-19 | 2025-03-22
Activity 4: Scrum #3 | 2 days | 2025-03-23 | 2025-03-24
MVP 3: Documentation and Reporting (Ongoing)
Work Package 3.1: Code Documentation | Ongoing | 2025-02-10 | 2025-04-05
Work Package 3.2: User Guide | 3 days | 2025-03-25 | 2025-03-27
Work Package 3.3: Research Paper | Various sections | 2025-02-20 | 2025-04-03
MVP 4: Delivery
Work Package 4.1: MVP Integration and Testing | 2 days | 2025-04-04 | 2025-04-05
Prepare and rehearse MVP demo | 1 day | 2025-04-06 | 2025-04-06
Activity 5: Project Submission | 2 days | 2025-04-04 | 2025-04-05
Final presentation & submission | 1 day | 2025-04-07 | 2025-04-07