## Tasks
Title | Status | Priority | Assigned To | Start Date | End Date | Description
MVP 1: Simulation Environment Setup
Work Package 1.1: Development Environment Setup | Active | Normal | Muhammad Hamza Shahab | 2025-02-10 | 2025-02-10
Work Package 1.2: Core Simulation Framework Implementation | Active | Normal | Muhammad Hamza Shahab | 2025-02-11 | 2025-02-18
Work Package 1.3: Data Input/Output Modules | Active | Normal | Syed Haider Abbas Naqvi | 2025-02-18 | 2025-02-20
Work Package 1.4: Visualization Module | Active | Normal | Syed Haider Abbas Naqvi | 2025-02-21 | 2025-02-23
MVP 2: Algorithm Implementation & Evaluation
Work Package 2.1: Embedding Policy Implementation | Active | Normal | Muhammad Hamza Shahab | 2025-02-25 | 2025-02-27
Work Package 2.2: Redundancy Optimization Algorithm (PSO) | Active | Normal | Muhammad Hamza Shahab | 2025-02-28 | 2025-03-04
Work Package 2.3: Performance Metric Calculation | Active | Normal | Syed Haider Abbas Naqvi | 2025-03-05 | 2025-03-07
Work Package 2.4: Algorithm Comparison & Evaluation | Active | Normal | Syed Haider Abbas Naqvi | 2025-03-11 | 2025-03-18
Work Package 2.5: Other Redundancy Optimization Algorithms | Active | Normal | Muhammad Hamza Shahab | 2025-03-19 | 2025-03-22
MVP 3: Documentation and Reporting (Ongoing)
Work Package 3.1: Code Documentation | Active | Normal | Muhammad Hamza Shahab | 2025-02-10 | 2025-04-05
Work Package 3.2: User Guide | Active | Normal | Syed Haider Abbas Naqvi | 2025-03-25 | 2025-03-27
Work Package 3.3: Research Paper | Active | Normal | Muhammad Hamza Shahab | 2025-02-20 | 2025-04-03
MVP 4: Delivery
Work Package 4.1: MVP Integration and Testing | Active | Normal | Muhammad Hamza Shahab | 2025-04-04 | 2025-04-05
Prepare and rehearse MVP demo | Active | Normal | Muhammad Hamza Shahab | 2025-04-06 | 2025-04-06